## Task List
Wedding Task List
Key Dates
| Wedding | 2006-10-01
Due Date | Primary | Secondary | Action Item
2006-01-04 |  |  | Learn the facts about diamonds, and find the engagement ring.
2006-01-04 |  |  | Propose.
2006-01-04 |  |  | Set an initial budget.
2006-01-04 |  |  | Select a wedding date and time.
2006-01-04 |  |  | Announce your engagement in the newspaper.
2006-01-04 |  |  | Determine the type of wedding you want (day/night, indoor/outdoor, formal/causl).
2006-01-04 |  |  | Research availability of reception locations.
2006-01-04 |  |  | Select and book your reception location, or get a tent if that is what you decided upon
2006-01-04 |  |  | Find a caterer if not already provided by the reception facility.
2006-01-04 |  |  | Research availability of ceremony locations, if not included with your reception site.
2006-01-04 |  |  | Select and book your ceremony location.
2006-01-04 |  |  | Determine who will officiate at the ceremony, if not provided with the ceremony location.
2006-01-04 |  |  | Determine how many guests you wish to invite.
2006-01-04 |  |  | Set aside blocks of hotel/motel rooms for out-of-town guests.
2006-01-04 |  |  | Get a band or DJ, get one early because they can get booked quickly.
2006-01-04 |  |  | Decide if you want a bridal party, and if so, then how large.
2006-01-04 |  |  | Start to research your bridal gowns.
2006-01-04 |  |  | Start to research the grooms formal wear/tuxedo.
2006-01-04 |  |  | Start to research bridesmaids' dresses.
2006-01-04 |  |  | Start to research formal wear for the groomsmen.
2006-01-04 |  |  | Compare and find a photographer.
2006-01-04 |  |  | Compare and find a videographer.
2006-01-04 |  |  | Find local florists and set appointments to look at their work
2006-01-04 |  |  | Be sure that you get contracts from all the professionals you choose.
2006-01-04 |  |  | Create a bridal registry, and/or an engagement registry.
2006-01-04 |  |  | Visit bridal shows. Check the schedule of upcoming bridal shows in your areas.
6 months
2006-04-04 |  |  | Start compiling the guest list (inform your families to do the same).
2006-04-04 |  |  | Select the attendants for your wedding party.
2006-04-04 |  |  | Purchase the bride's gown.
2006-04-04 |  |  | Purchase the groom's tuxedo.
2006-04-04 |  |  | Purchase bridesmaid's dresses.
2006-04-04 |  |  | Arrange for you groomsmen to be measured and reserve the tuxedos.
2006-04-04 |  |  | Shop for the wedding dress, headpiece, veil, and other accessories.
2006-04-04 |  |  | Start planning for honeymoon, research you destinations.
2006-04-04 |  |  | Choose and reserve your florist.
2006-04-04 |  |  | Order the wedding cake, if not privded by the caterer or reception hall.
2006-04-04 |  |  | The parents of the groom should begin to arrange the Rehearsal Dinner, and reserve a restaurant or make other arrangements.
2006-04-04 |  |  | Arrange for transportation for the wedding. Limousines, Horse & Carriage, vans, etc.
4 months
2006-06-03 |  |  | Make appointments for a physical exam with your doctor/dentist.
2006-06-03 |  |  | Check requirements for blood test and marriage license in your state.
2006-06-03 |  |  | Shop for wedding rings
2006-06-03 |  |  | Select and order the invitations and stationery.
2006-06-03 |  |  | Make sure all the men's attire has been ordered.
2006-06-03 |  |  | Decide where to live after the wedding.
2006-06-03 |  |  | Complete the guest lists.
2006-06-03 |  |  | Begin shopping for trousseau.
2006-06-03 |  |  | Send your engagement announcement to the newspaper.
2006-06-03 |  |  | Inform mothers to select their dresses.
2006-06-03 |  |  | Select and order the men's attire.
2006-06-03 |  |  | Finalize honeymoon details and make the necessary reservations.
2 months
2006-08-02 |  |  | Confirm the menu and catering details with the caterer.
2006-08-02 |  |  | Prepare all maps and directions for the ceremony and reception.
2006-08-02 |  |  | Select your wedding rings.
2006-08-02 |  |  | Buy a wedding guest book.
2006-08-02 |  |  | Set the dates and times with the officiant for the rehearsal.
2006-08-02 |  |  | Plan the bridesmaids' luncheon and any other parties.
2006-08-02 |  |  | Determine your resources for designing and printing the program for the ceremony.
2006-08-02 |  |  | Finalize the florist details, photographer, videographer, musicians, etc.
2006-08-02 |  |  | Arrange the ncessary accomodations for out-of-town guests.
2006-08-02 |  |  | Plan a rehearsal dinner, time and place.
2006-08-02 |  |  | Confirm the wedding cake details with the baker.
6 weeks
2006-08-20 |  |  | Mail invitations and announcements.
2006-08-20 |  |  | Prepare a portrait for the newspaper. Check your local newspaper for details and timing.
2006-08-20 |  |  | Set appointment with photographer for your formal bridal portrait.
2006-08-20 |  |  | Hire the limousine or other forms of transportation for the wedding.
4 weeks
2006-09-03 |  |  | Decide what your menu is going to be for the reception. Estimate the expected number of guests.
2006-09-03 |  |  | Buy a gift for the groom.
2006-09-03 |  |  | Schedule a final fitting for your gown so it can be ready for your formal bridal portrait.
2006-09-03 |  |  | Purchase a going away outfit.
2006-09-03 |  |  | Pick up your wedding rings.
2006-09-03 |  |  | Purchase (borrow) all wedding accessories such as the ring pillow, goblets, garter belt, candles, etc.
2006-09-03 |  |  | Confirm florist details and delivery times.
2006-09-03 |  |  | Plan the seating for the reception as well as other details for the ceremony and reception.
2006-09-03 |  |  | Start writing placement cards.
2006-09-03 |  |  | Make sure all bridesmaids' attire has been fitted.
2006-09-03 |  |  | Buy a gift for the bride.
2006-09-03 |  |  | Choose the music for your ceremony, first dance, parent dances, and party and give information to band, dj, or other musicians.
2 weeks
2006-09-17 |  |  | Make arrangements to have your wedding gifts moved to your new home.
2006-09-17 |  |  | Handle business and legal details such as name changes, address, changes, etc.
2006-09-17 |  |  | Prepare the wedding announcement for the newspaper.
2006-09-17 |  |  | Reconfirm your guests' accomodations.
2006-09-17 |  |  | Make sure all clothing and accessories for you and the bridal party are ready.
2006-09-17 |  |  | Get your marriage license and any blood tests which are needed.
1 week
2006-09-24 |  |  | Review any seating details with the ushers.
2006-09-24 |  |  | Make sure all wedding attire fits.
2006-09-24 |  |  | Finalize the seating arrangements.
2006-09-24 |  |  | Reconfirm your honeymoon reservations. Ensure you have any necessary plane tickets.
2006-09-24 |  |  | Start packing for your honeymoon.
2006-09-24 |  |  | Call any guests who have not responded yet.
2006-09-24 |  |  | Finish all the place cards for the reception.
2006-09-24 |  |  | Review all the final details with your photographer, videographer, etc.
2006-09-24 |  |  | Give a final head count to the caterer.
2006-09-24 |  |  | Confirm the availability of the musicians and vocalists.
2006-09-24 |  |  | Delegate responsibilities to reliable individuals on your wedding day.
2006-09-24 |  |  | Wrap and present the wedding party gifts.
2006-09-24 |  |  | Finalize your rehearsal dinner arrangements or other plans.
1 day
2006-09-24 |  |  | Get a manicure or massage to relax yourself.
2006-09-24 |  |  | Stay with your family the night before and sleep early.
2006-09-24 |  |  | Review and rehearse all the details of your participants.
The Big Day
2006-10-01 |  |  | Make sure the best man and maid of honor sign the wedding certificate
2006-10-01 |  |  | Allow yourself plenty of time to get dressed.
2006-10-01 |  |  | Be sure to eat properly.
2006-10-01 |  |  | Rest and relax with a good bath.
2006-10-01 |  |  | Prepare for your hairdresser and makeup appointments.
2006-10-01 |  |  | Enjoy your wonderful wedding and cherish each and every moment!