## Project Timeline
Project Name - Timeline |  |  |  | 2015 | [25 empty] | 2016
|  |  |  | JUL |  |  |  | AUG |  |  |  | SEP |  |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  |  | JAN |  |  |  | FEB
Deliverables |  | Owner | Duration | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Planning phase |  |  | 3 w | bar: JUL W2 to JUL W4
| Task I | owner | 2 w | bar: JUL W2 to JUL W3
| Task II | owner | 3 w | bar: JUL W2 to JUL W4
| Task III | owner | 1 w | bar: JUL W4
Team phase |  |  | 3 w | bar: AUG W1 to AUG W3
| Task I | owner | 2 w | bar: AUG W1 to AUG W2
| Task II | owner | 1 w | bar: AUG W2
| Task III | owner | 1 w | bar: AUG W3
Prototype phase |  |  | 7 w | bar: AUG W4 to OCT W1
| Task I | owner | 1 w | bar: AUG W4
| Task II | owner | 3 w | bar: SEP W1 to SEP W4
| Task III | owner | 2 w | bar: SEP W2 to SEP W3
| Task IV | owner | 2 w | bar: SEP W3 to SEP W4
| Task V | owner | 2 w | bar: SEP W5 to OCT W1
Implementation phase |  |  | 9 w | bar: OCT W2 to DEC W2
| Task I | owner | 4 w | NOV W1: 2
| Task II | owner | 1 w | bar: OCT W4
| Task III | owner | 7 w | bar: OCT W4 to DEC W2
| Task IV | owner | 6 w | bar: NOV W1 to DEC W2
| Task V | owner | 2 w | bar: DEC W1 to DEC W2
| Task VI | owner | 2 w | DEC W1: 3; DEC W2: 3
Closure phase |  |  | 5 w | bar: DEC W3 to JAN W2
| Task I | owner | 5 w | bar: DEC W3 to JAN W2
| Task II | owner | 5 w | bar: DEC W3 to JAN W2
Annotations |  |  |  | SEP W2: 1; SEP W3: Deadline extended by 2 weeks
[21 empty] | 2 | External dependency
[25 empty] | 3 | Critical